MVUCC Meeting - November 21, 2017

Meeting called to order at 10:12 A.M. by Gary Earl, President MVUCC

Self introductions

Financial Report - Gary

Downtown Twin Falls project update - Nothing new since last meeting.

HWY 93 Project - Scott Watkins, Track - Conduit and 200 Pair cable in. Will be trenching about 300 feet and planning for a cutover on the South End of the project. Still more work to be done.

Jeff Schamber, PMT, will be moving traffic over about mid December.

Brack McMurtrey, ITG, ITG has a gas line that will need to be moved. Please coordinate with the other utilities for a common goal/move. ITG appears to be nine plus feet deep in a specific area

HWY 93 South - culverts are currently being replaced between Hollister and Deep Creek. Adding shoulders and widening the road through this area. All culverts, except A Line canal, have been replaced and/or moved. Will be coordinating with Idaho Power for an outage to take care of the A Line culvert. Filer is currently moved and out of the area.

Construction Updates

Filer - ground work is basically done for the year. Working on planning next years projects. Currently moving customers to fiber in Filer

PMT - Working on drops in the Rupert Project. Trying to finish up

Extreme Excavating - City of Rupert working on a large overhaul of roads, subdivisions

Tesoro - Nothing to report

PMT - Twin Falls, finishing projects for the year

Track - Verizon project, subdivision south of Burley 200 S 85 E, direct bury fiber. Lots of projects

Idaho Power - Subdivisions in Twin - more smaller projects in Town

ITD - New project coming on HWY 93 from 5 miles south of Shoshone, utility poles to be relocated. Question about a project on HWY 26, rebuild of a culvert and will need a temp relocation of power for a crane. Salmon Falls Creek, 2019 project, will need a temporary relocation of Century Link and Syringa Networks.

ITG - Hankins Road is about done. Lots of subdivisions wanting gas services. Joint Trench committee is going gangbusters. Common trench provided by customers is beneficial for all. 300 S near Jerome, replacing a high pressure valve. In Burley, McCains, gas from 100 S 200 W to HWY30 and onto McCains for expansion of service. Deadline of May/June. ITG will be going to a contractor from out of state. HWY 93 crossing near the Fish and Game. Bridge Crossing in Jerome, Z Canal, will be a 2019 ITD project. ITD starting communication with ITG now.

Gary Earl spoke with Gary Lancaster and a joint trench will be started in the Golden Spur area next month to finish about 20-25 lots.

Gary Earl spoke about the interior portion of Filer being completed for a fiber overbuild. Will be front access going forward. Will get with Brack later to work along with Mid States Engineering.

General Discussion

Damage Prevention documentation... Who is currently doing it or hearing from the Damage Prevention Board on hits?

ITG has a standing 2nd Thursday of each month for Damage Prevention training.

December 19th will be our next meeting date.

End of February, first of March for our Contractor appreciation breakfast at the Red lion. Will start looking at dates to get information out to the contractors for advanced notice.

Meeting adjourned at 10:40 A.M.