## Slide 1: Gas Facility Replacement Program aka Aldyl A Pipe Replacement Program Main Pipe Replacement & Service Tee Transition Rebuilds (STTR)
2016 NWUCC JOINT STATES MEETING September 29, 2016

## Slide 2
OVERVIEW
MANAGING
THE ASSETS
DIMP & PRIORITIZATION
SCOPE & REACH
20 YEAR PLAN & MILESTONES
CONSTRUCTIONMETHODS
WHAT
WHY
WHERE
WHEN
HOW
PERFORMANCE
& COSTS
CUSTOMER CARE
RESULTS
Notes: CONSTRUCTION, LEVERAGING TECHNOLOGY & COST CONTROL

## Slide 3: MANAGING THE ASSETS
MAIN PIPE
1 ¼” TO 4” DIAMETER PIPE
INSTALLED 1964 TO 1987
REPLACEMENT OF MAIN PIPE & SERVICE TOWERS
SERVICE TEE TRANSITION REBUILD (STTR)
ALDYL A SERVICE PIPE AT STEEL TEE LOCATED ON STEEL MAIN
MAIN PIPE & PRIORITY SERVICES
Notes: WHAT – Managing the Assets
PROACTIVE PROGRAM DESIGNED TO:
737 MILES OF MAIN PIPE AT START OF THE PROGRAM
NEARLY 18,000 STTRS AT START OF PROGRAM

## Slide 4
PROTOCOL FOR MANAGING ALDYL ‘A’ PIPE
AVISTA ASSET MANAGEMENT
(FEBRUARY 2012)
20 YEAR TIME FRAME IS OPTIMUM
DISTRIBUTION INTEGRITY MANAGEMENT PLAN (DIMP)
ASSET MANAGEMENT ANALYSIS – DIMP & PRIORITIZATION
LEAK SURVEYS CONTINUE TO CAPTURE NEW DATA & IDENTIFY THREATS
KNOW WHAT IS IN YOUR SYSTEM
IDENTIFY THREATS
EVALUATE & RANK RISKS
IDENTIFY & IMPLEMENT MEASURES TO REDUCE RISK
MEASURE / MONITOR & EVALUATE EFFECTIVENESS
REPORT RESULTS
TOP 29 PROJECT AREAS GEOSPATIALLY LOCATED IN GIS USING RISK DATA
Notes: WHY – Asset Management analysis shows the failure rates & indicates:
20 YEAR TIME FRAME IS OPTIMUM TO MANAGE MAIN PIPE RISK & SPEND
DIMP – Federally Mandated in 2011

## Slide 5
= LOWER QUANTITY
= DENSE QUANTITY
SCOPE & REACH
Chart: MAIN PIPE (MILES)
| WASHINGTON | OREGON | IDAHO
MAIN PIPE | 355 | 252 | 130
Chart: 
| WASHINGTON | OREGON | IDAHO
STTR'S | 7442 | 7167 | 3160
Notes: WHERE IT IS
MAIN PIPE 737 MILES (20 YEARS)
STTR’S 17,769 (5 YEARS)
5

## Slide 6: 2016 MAJOR PROJECTS
N. SPOKANE MAIN PIPE (5.56 MI)
FAIRWOOD E. MAIN PIPE (4.14 MI)
EAST MEDFORD MAIN PIPE (4.59 MI)
CLARKSTON & ADJ. STTR (388)
SPOKANE S.H. & ADJ. STTR (770)
KLAMATH FALLS STTR (≈1,000 UNITS)
KLAMATH FALLS MAIN PIPE (4.98. MI)
MOSCOW & ADJ. STTR (316)
PULLMAN & ADJ. STTR (419)
KELLOGG & ADJ. STTR (197)
DEER PARK STTR (66)
COLVILLE/CHEWELAH STTR (229)
GENESSE, ID (5.46 MI)
2016 OVERVIEW
  MAIN PIPE:
  24.73 MILES
SCOPE
  STTR’S:
  ≈ 3,385 UNITS
13 MAJOR PROJECTS
39 MUNICIPAL JURISDICTIONS
Notes: WHERE – Aldyl A is throughout our system. This is what 2016 looks like – As you can see we are spread out across much of our territory
In future years we be even more spread out since we will have worked through the densely concentrated neighborhoods.
Currently our contractor NPL employs approximately 130-150 (170 total) people and the GFRP Team is 11. That is a >12:1 Ratio of NPL to Avista
6

## Slide 7: PROGRAM MILESTONES
24
PROJECTS COMPLETED
4 YEAR CONTRACT CYCLE
(2028 – 2031)
5 YEAR CONTRACT CYCLE
(2013 – 2027)
5 YEAR CONTRACT CYCLE
(2018 – 2022)
13
2016 MAJOR PROJECTS
5 YEAR CONTRACT CYCLE
(2013 – 2017)
TODAY
MAIN PIPE PROGRAM ENDS
≈ 30
MAJOR PROJECTS
45 MILES/YEAR
2018
2013
2023
2028
2031
STTR PROGRAM ENDS
7
2017 MAJOR PROJECTS
≈ 30
MAJOR PROJECTS
45 MILES/YEAR
≈ 30
MAJOR PROJECTS
45 MILES/YEAR
Notes: WHEN = Milestones
7

## Slide 8
GREATEST FOOTPRINT
OPEN TRENCH EXCAVATION
MINIMAL FOOTPRINT
HORIZONTAL DIRECTIONAL DRILL (HDD)
MINIMAL FOOTPRINT
SPLIT & PULL
LEVERAGING TECHNOLOGY- MAJOR MAIN PIPE PROJECTS
Notes: HOW
8

## Slide 9
KEYHOLE TECHNOLOGY & MAIN PIPE PROJECTS
SUPPORTS MAIN PIPE HDD/BORE OPERATIONS
KEYHOLE TECHNOLOGY
SPOTTING CROSSING UTILITIES SAFELY
SOFT EXCAVATION
Notes: HOW
9

## Slide 10
LEVERAGING TECHNOLOGY (STTR)
URBAN MICRO-SURGERY
KEYHOLE TECHNOLOGY
SAFE EXCAVATION
VACUUM EXCAVATION
GREATEST DISTURBANCE
HARD SURFACE CUT & PATCH
RE-INSTATED CORE
REBUILD ASSEMBLY
SOFT SURFACE BELL HOLE
Notes: HOW
10

## Slide 11: LEVERAGING TECHNOLOGY – 2015 RESULTS
Chart: MAIN PIPE
| MEDFORD - MEDFORD EAST | SPOKANE - DEER PARK | SPOKANE - FAIRWOOD | 2015 AVERAGE | CDA IDAHO - POST FALLS | SPOKANE - WOODRIDGE
HDD/BORE | 0.18 | 0.25 | 0.44 | 0.452 | 0.56 | 0.83
SPLIT & PULL | 0 | 0.06 | 0 | 0.026 | 0.01 | 0.06
OPEN TRENCH | 0.82 | 0.69 | 0.56 | 0.522 | 0.43 | 0.11
Chart: STTR
| LAGRANDE, OREGON | 2015 AVERAGE | LEWISTON, IDAHO | SPOKANE VALLEY, WA. | MEDFORD, OREGON
KEYHOLE | 0.07 | 0.47 | 0.56 | 0.62 | 0.63
CONVENTIONAL CUT/PATCH | 0.01 | 0.07 | 0.1 | 0.14 | 0.03
SOFT SURFACE | 0.92 | 0.46 | 0.34 | 0.24 | 0.34
Notes: HOW
2014 AVERAGE FOR MAIN PIPE WAS:
HDD/BORE -
SPLIT & PULL -
OPEN TRENCH -
11

## Slide 12: MAIN PIPE - SYSTEM WIDE RESULTS 2012 – AUG. 2016
Chart: SYSTEM WIDE - MAIN PIPE COMPLETED VS. PLANNED MILES
| 2013 | 2014 | 2015 | 2016
COMMITTED | 11.3 | 16.9 | 18.3 | 19.1 | 24.7 | 26.8
PLANNED | 11.3 | 16.9 | 18.3 | 19.1 | 19.7 | 20.4
MILES COMPLETED | 12.3712 | 19.4564 | 22.3358 | 20.4 | 17.38
Chart: SYSTEM WIDE - MAIN PIPE COMPLETED VS. PLANNED MILES
| 2013 | 2014 | 2015 | 2016
COMMITTED | 11.3 | 16.9 | 18.3 | 19.1 | 24.7 | 26.8
PLANNED | 11.3 | 16.9 | 18.3 | 19.1 | 19.7 | 20.4
MILES COMPLETED | 12.3712 | 19.4564 | 22.3358 | 20.4
Chart: 
| Miles Complete | Miles Remaining
 | 84.01 | 645.0566
Notes: RESULTS – SCOPE – WE CONTINUE TO STAY AHEAD OF THE QUANTITIES THAT WE STATE TO THE COMMISSIONS
DELTA BETWEEN 2012-2015 TOTALS SHOWN IN BAR CHART & 82.5 IN PIE CHART IS THE 2011 ODESSA PROJECT.
STAYING AHEAD OF UTITLIY COMMISSION COMMITMENTS
12

## Slide 13: STTR - SYSTEM WIDE RESULTS 2012 – AUG 2016
Chart: SYSTEM WIDE - STTR COMPLETE VS. PLANNED
PLANNED | 2150 | 3473 | 3473 | 3473 | 3473
REVISED PLANNED | 2150 | 3473 | 3473 | 3385 | 852
COMPLETED | 2116 | 5308 | 5750 | 2389
Chart: STTR COMPLETED & OUTLOOK
| COMPLETE 2012- AUG 2016 | REMAINING 2016 | PLANNED 2017
Actual STTR Complete | 15733 | 1055 | 852
Notes: RESULTS – SCOPE -
36.76 MILES OF MAIN PIPE REMAIN OF THE ORIGINALLY PLANNED 57.64 MILES BUT WE HAVE INCREASED THE MILES BY XX TO 48.16 MILES WITH 11.4 MILES OVER 2016-2017
THIS INCREASE IS TO COMPENSATE FOR THE REDUCTION IN STTRS OF APPROX. XXXX UNITS
NEED TO ADD ALL PAPER FIELDED UNITS
13

## Slide 14: PROGRAM BUDGET RESULTS 2012 – AUG 2016
Chart: CAPITAL BUDGET RESULTS
| 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018
BUDGET | 5000000 | 12000000 | 16452196 | 19547429 | 21885272 | 21762977 | 20700000
ACTUAL | 4643188 | 13205373 | 16917201 | 19724120 | 21000000
VARIANCE | -0.071362 | 0.10045 | 0.028264 | 0.0090391
≈ $ 75 M
INVESTED
2012 - 2016
2012 2013 2014 2015 2016 2017 2018
Notes: RESULTS – BUDGET - Here is the Capital Spend (Plan to Actual) results – with the budget variance by (%) percent shown at the bottom
THE GFRP REPRESENTS 5% OF AVISTA’S ANNUAL CAPITAL BUDGET
14

## Slide 15
PRE-CONSTRUCTION PHASE
MUNICIPAL ROAD PROJECT COORDINATION
PERMIT COORDINATION
TOWN HALL MEETINGS
INTERNAL COORDINATION
CONSTRUCTION PHASE
CUSTOMER
LETTERS
PHONE
CALLS
PERSONAL
CONTACT
DOOR
HANGERS
RE-LIGHT
APPLIANCE
CUSTOMER CARE - COMMUNICATION
WEB
PAGE
Notes: CUSTOMER CARE
WE COME TO THESE AREAS UNINVITED AND CREATE A LOT OF DISRUPTION IN THE ROADWAYS, AND EVEN CUSTOMER YARDS/DRIVEWAYS, ETC. WE COORDINATE WITH CUSTOMERS TO AND ENTER MOST HOMES TO RE-LIGHT APPLIANCES. DESPITE THE LEVEL OF DISRUPTION & INCONVENIENCE, THROUGH A WELL THOUGHT OUT COMMUNICATION PLAN, WE HAVE BEEN ABLE TO MINIMIZE CUSTOMER DISATISFACTION AND COMPLAINTS.
Customer Communication is a crucial component of the program and the projects. We utilize a communication tool –kit which is tailored to each project. Generally, the tool kit includes the items represented above.

## Slide 16: CUSTOMER CARE
Chart: CUSTOMERS CONTACTED VS. COMPLAINTS
| COMPLAINTS | NO COMPLAINTS
Column1 | 0.008 | 0.992
Notes: CUSTOMER CARE
2014 COMPLAINTS = < 1% AT .12 OF A %
2015 WAS EVEN BETTER WITH = < 1% AT .08 OF A %
2016 OF 13,247 PEOPLE (6,566 CUSTOMERS / 6,771 NEIGHBORING PROPERTIES) CONTACTED ONLY 5 COMPLAINTS HAVE BEEN LOGGED IN 2016
16

## Slide 17
Q & A